## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Set up the project environment for RAG chatbot | MUST HAVE | Google colab | Debalina Chakraborty | 3- Completed
S2 | S2 | US-002 | Choose the retrieval mechanism, integrating relevant databases and APIs for RAG chatbot. | MUST HAVE | Groq cloud, Hugging face, FAISS, | Debalina Chakraborty | 3- Completed
S3 | S3 | US-003 | Integrate the generation component for the chatbot to process retrieved data and form responses. | MUST HAVE | US-002 | Debalina Chakraborty | 3- Completed
S4 | S4 | US-004 | Create UI for Chatbot and perform testing on it to validate functionality and accuracy, and make necessary adjustments. | MUST HAVE | Gradio | Debalina Chakraborty | 3- Completed
S5 | S5 | US-005 | Set up the project environment for Pandas AI agent | MUST HAVE | Google colab | Debalina Chakraborty | 3- Completed
S6 | S6 | US-006 | Integrate the generation component for the Agent to process retrieved data and form responses. | SHOULD HAVE | Groq cloud, Hugging face, FAISS, | Debalina Chakraborty | 3- Completed
S7 | S7 | US-007 | Integrate Pandas AI agent with external data sources | SHOULD HAVE | External data source | Debalina Chakraborty | 3- Completed
S8 | S8 | US-008 | Final testing, optimization, and deployment of Pandas AI agent. Document the entire workflow. | MUST HAVE | US-005 - US-007 | Debalina Chakraborty | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 29 | 3 | 3 | 1 | 1 | 3 | 2 | 2 | 3 | 3 | 1 | 1 | 2 | 2 | 2
SPRINT BACKLOG
US-001 | T1 | Set up project repository and version control | 2024-11-04 | 2024-11-04 | Debalina Chakraborty | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T2 | Install dependencies and configure environment (Python, libraries, etc.) | 2024-11-05 | 2024-11-06 | Debalina Chakraborty | Build | 3- Completed | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T3 | Connect to databases or external APIs | 2024-11-07 | 2002-11-08 | Debalina Chakraborty | Coding | 3- Completed | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T4 | Validate data retrieval accuracy and performance | 2024-11-11 | 2024-11-12 | Debalina Chakraborty | Regression Test | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-003 | T5 | Develop generation component for RAG chatbot | 2024-11-12 | 2024-11-13 | Debalina Chakraborty | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
US-003 | T6 | Integrate the generation and retrieval components | 2024-11-14 | 2024-11-15 | Debalina Chakraborty | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
US-004 | T7 | Perform testing of RAG chatbot | 2024-11-18 | 2024-11-19 | Debalina Chakraborty | Regression Test | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
US-004 | T8 | Gather feedback and analyze results from testing | 2024-11-20 | 2024-11-21 | Debalina Chakraborty | Others | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T9 | Set up Pandas AI agent environment | 2024-11-25 | 2024-11-26 | Debalina Chakraborty | Build | 3- Completed | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T10 | Develop generation component for the Agent | 2024-11-27 | 2024-11-28 | Debalina Chakraborty | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T11 | Design and develop a user interface for the Pandas AI agent | 2024-11-29 | 2024-12-02 | Debalina Chakraborty | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
US-006 | T12 | Test the UI for functionality and usability, and refine based on feedback. | 2024-12-03 | 2024-12-04 | Debalina Chakraborty | Regression Test | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
US-007 | T13 | Integrate Pandas AI agent with external data sources (APIs, databases, etc.) | 2024-12-05 | 2024-12-06 | Debalina Chakraborty | Coding | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T14 | Perform final testing of the Pandas AI agent. | 2024-12-09 | 2024-12-10 | Debalina Chakraborty | Regression Test | 3- Completed | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T15 | Prepare and finalize project documentation for Pandas AI agent. | 2024-12-11 | 2024-12-12 | Debalina Chakraborty | Others | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0